## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | Group O | Phase 2 Progress Summary
Project Title | Multi-Site and Environmental Monitoring System | Total tracked items | 12
Stakeholder / Organisation | Goitemang Diane(Department of Agriculture, Plant and Science) | Completed | 12
Group Leader | Nido Maphosa | In Progress | 0
Number of Group Members | 8 | Blocked | 0
GitHub Repository Link | https://github.com/Nido-Maphosa86/soil-sensor-monitoring | Average completion | 100%
Reporting Period | 15 September-13 October 2026
Overall Phase Status | Completed | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Tyam M | 2026-09-15 | 2026-09-17 | Completed | 100% | https://github.com/Nido-Maphosa86/soil-sensor-monitoring
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Mjiyakho T, Tyam M, Machedi M | 2026-09-18 | 2026-09-25 | Completed | 100%
P2-03 | Sequence Diagram 1 | Important Flutter process | Mjiyakho | 2026-09-18 | 2026-09-25 | Completed | 100%
P2-04 | Sequence Diagram 2 | Important ASP.NET process | Mjiyakho | 2026-09-18 | 2026-09-25 | Completed | 100%
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Mjiyakho T | 2026-09-25 | 2026-09-30 | Completed | 100%
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Mjiyakho T, Masita T, Pikwa A, Seiphetlho GK | 2026-10-26 | 2026-10-05 | Completed | 100%
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Nido Maphosa, Freeman C, Tyam M, Machedi M | 2026-09-13 | 2026-10-06 | Completed | 100%
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces | Masita T | 2026-10-01 | 2026-10-02 | Completed | 100%
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Nido Maphosa, Pikwa A | 2026-10-12 | 2026-10-12 | Completed | 100%
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Freeman C, Seiphetlho GK | 2026-09-15 | 2026-10-13 | Completed | 100%
P2-11 | GitHub | Current design documentation and repository organisation | Nido Maphosa | 2026-10-09 | 2026-10-13 | Completed | 100%
P2-12 | Phase 2 Presentation | Presentation and defence preparation | N Maphosa, Freeman C, Tyam M, Machedi M, Masita T, Mjiyakho T, Pikwa A, Seiphetlho GK | 2026-10-14 | 2026-10-15 | Completed | 100%

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
Nido Maphosa | 223039784 | Web and Mobile Application Prototype | Organise the overall design for both the web and mobile applications and assign screens to members. | Organised the web and mobile application prototypes and worked on designing and arranging the web application screens. | 2026-10-12 | 15hrs |  | Yes | 2026-09-21 |  | Completed
Freeman C | 224097774 | Microsoft Project Schedule and Web Application Prototype. | Manage and update the project schedule using Microsoft Project and design the Web application prototype screens. | Updated and maintained the Microsoft Project schedule and designed the web application prototype screens. | 2026-10-12 | 18hrs |  | Yes | 2026-10-12 |  | Completed
Pikwa A | 224135694 | Mobile Application Prototype | Design the mobile application screens. | Designed the mobile application prototype screens and worked on Updating the SRS | 2026-10-07 | 10hrs |  | Yes | 2026-10-09 |  | Completed
Tyam M | 222056708 | System Architecture and Web Application Prototype | Develop the system architecture and contribute to the design of the web application screens. | Worked on the system architecture and designed the web application prototype screens. | 2026-09-18 | 14hrs |  | Yes | 2026-09-21 |  | Completed
Mjiyakho T | 222088478 | Mobile Application Prototype, ERDs | Identify database entities, attributes, primary keys, foreign keys, relationships and cardinalities. | Identified and documented the database entities, their attributes, primary and foreign keys, and the relationships and cardinalities between entities. | 2026-09-30 | 18hrs |  | Yes | 2026-10-02 |  | Completed
Machedi M | 222001607 | Use Case diagrams and Web application Prototype | Identify System actors and their interactions with the web and mobile applications and contribute to the web application screens. | Worked on identifying system actors and their interactions with the web and mobile applications, developed the use cases diagrams, and contributed to the design of the web application screens. | 2026-09-25 | 15hrs |  | Yes | 2026-09-28 |  | Completed
Masita T | 223043636 | Mobile Application Prototype | Design and develop the prototype screens for the mobile application. | Designed and developed the mobile application prototype screens and helped with the use cases. | 2026-10-07 | 10hrs |  | Yes | 2026-10-12 |  | Completed
Seiphetlho Gk | 224130045 | Mobile Application Prototype, Progress Report | Compile and update the Phase 2 progress report and contribute to the design of the mobile applications screens. | Updated and maintained the Phase 2 progress report by documenting project progress and activities, and worked on designing the mobile application prototype screens. | 2026-10-13 | 13hrs |  | Yes | 2026-10-12 |  | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | Figma | Web Application – Figma | Yes | 2026-10-13 | Tyam M | Yes
Use Case Diagram | Figma | Web Application – Figma | Yes | 2026-10-13 | Machedi M | Yes
Sequence Diagram 1 | Figma | Web Application – Figma | Yes | 2026-10-13 | Mjiyakho T | Yes
Sequence Diagram 2 | Figma | Web Application – Figma | Yes | 2026-10-13 | Mjiyakho T | Yes
ERD | Figma | Web Application – Figma | Yes | 2026-10-13 | Mjiyakho T | Yes
Flutter Interface Designs | Figma Prototype | Mobile - Screens | Yes | 2026-10-13 | Seiphetlho G, Pikwa A, Masita T, Mjiyakho T | Yes
ASP.NET Interface Designs | Figma Prototype | Web Application - Screens | Yes | 2026-10-13 | Maphosa N, Tyam M, Freeman C, Machedi M | Yes
Navigation Flow | Figma | https://www.figma.com/design/KmYxvZZnIxJXbAuP3n39Hb/Web-Application?node-id=6-15&p=f&t=PMWls9wQ4muboydr-0 | Yes | 2026-10-13 | Tyam M, Maphosa N | Yes

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
2026-09-19 | Ensuring that the database design included the correct entities, attributes, keys, and relationships. | The database design required careful review before it could be incorporated into the overall system design. | Identified the entities, attributes, primary keys, foreign keys, relationships, and cardinalities for the ERD | Nido Maphosa | 2026-09-19 | Completed | 2026-09-20
2026-09-21 | Designing consistent interfaces for the web and mobile applications. | Additional effort was required to organise the screens and ensure that the two interfaces supported the intended system functionality. | Collaborated on the prototypes, reviewed the screens, and refined the interface designs | Tyam, Freeman, Maphosa, Pikwa, Mjiyakho, Seiphetlho, Machedi, Masita | 2026-10-02 | Completed | 2026-10-07
2026-09-26 | Designing the mobile application screens and navigation flow | The mobile application required attention to screen arrangement and navigation between different sections. | Divided the work among the members so that the work would be easier. Designed and organised the mobile screens and reviewed the navigation flow. | Mjiyakho, Seiphetlho, Pikwa, Masita | 2026-10-26 | Completed | 2026-10-05
2026-10-09 | Incorporate stakeholder feedback into the designs | The team needed to review the proposed design and consider possible adjustments before finalising it. | The stakeholder reviewed the feedback and there was no necessary changes to the prototype and design documentation. | Nido Maphosa | 2026-10-05 | Completed | 2026-10-12
2026-09-28 | The project mentor was unavailable from 28 September to 2 September, preventing the team from attending consultations during that period. | The team had to postpone the consultation and wait until the mentor returned the following week to review our work and check if we are on the right track | Continued working on the available project activities and design tasks while waiting for the mentor to return, then resumed consultations when he became available. | Nido Maphosa | 2026-10-02 | Completed | 2026-10-09
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | 15 September-13 October 2026 | Phase 2 Completion Checklist | Complete?
Overall Phase Status | Completed | Architecture complete | Yes
What was completed during Phase 2? | Web and Mobile application prototype, system architecture, sequence diagrams, use case diagrams, ERD and project documentation. | Use Case Diagram complete | Yes
What remains incomplete? | Phase 2 presentation | Two Sequence Diagrams complete | Yes
Why is it incomplete? | It will take place on 13 October 2026 | ERD complete | Yes
Which contributions were particularly important? | Developing the prototypes, system architecture, UML diagrams, ERD, and maintaining the project schedule and progress report | Flutter interfaces complete | Yes
Were there participation concerns? | Participation was generally collaborative, although workload distribution and communication were not always balanced. | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? | Improve communication, provide regular updates, clarify responsibilities, and complete tasks on time. | Editable source links/files recorded | Yes
Main priority for Phase 3 | Begin development of the web and mobile applications using the approved designs and ensure both applications work as one integrated system | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | No
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | Yes

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
During Phase 2, the group successfully completed the design and prototyping activities required for the project. These included the web and mobile application prototypes, system architecture, sequence diagrams, use case diagrams, and the Entity Relationship Diagram (ERD). The group also worked on the system design to ensure that the web and mobile applications followed the intended system requirements and functionality. The prototypes helped the group and the stakeholder visualise how the applications would look and how users would interact with the system before moving into the development phase. The UML diagrams and ERD provided a clearer understanding of the system's structure, user interactions, and database relationships.
2. Which architecture or design activities were the most challenging?
The most challenging activities during phase 2 were designing the mobile application prototype, developing the use case diagrams and creating the ERD. Designing the mobile application required careful planning of the screens, layout and navigation to ensure that users could move between different sections easily. Developing the use case diagrams also required the group to identify the different actors and understand their responsibilities and interactions with the web and mobile applications.
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
The group used the Software Requirements Specification (SRS) as a guide to ensure that the Flutter mobile application and ASP.NET web application followed the same system requirements. The team also referred to the system architecture and sequence diagrams to understand the intended flow of information and interactions within the system. The group worked together and reviewed the different design components after completing each part. The backend design and application prototypes were used to maintain consistency in the system's structure, data and functionality. The mobile application screens and web application interfaces were designed around the same overall system requirements to ensure that both platforms would work together as parts of one integrated system. These design activities provided a common foundation for implementing and integrating the applications during Phase 3.
4. How was work divided among group members, and was participation balanced?
The work was divided among group members according to their assigned responsibilities, strengths and the different project deliverables. Some members focused on the web application prototype, while others worked on the mobile application prototype, system architecture, UML diagrams, ERD and project documentation. Certain members also assisted with managing the project schedule and updating the progress report. The group collaborated throughout the design process, and members were expected to complete their assigned tasks while assisting others when necessary. Some members worked together in pairs on the web and mobile application designs to help complete the work efficiently. Although the responsibilities were distributed among the members, participation was not always completely balanced, as some members had more work to complete than others. Communication between members was also a challenge at times. Nevertheless, the team continued working towards the common goal of completing the Phase 2 design deliverables.
5. What did the group learn from developing the UML, ERD and interface designs?
The group learned the importance of planning and understanding a system before beginning implementation. Developing UML diagrams helped members understand how different actors interact with the system, the responsibilities of each actor and the flow of activities within the applications. Creating the ERD improved the group's understanding of database design, including entities, attributes, primary keys, foreign keys and relationships between data. The interface design activities also helped members understand how users would interact with the web and mobile applications and how screen layouts and navigation contribute to usability. Furthermore, the group learned that effective communication, teamwork and reviewing each other's work are essential when developing a system. Careful planning during the design phase can help reduce confusion, identify potential problems early and save time during coding and implementation.
6. What will the group do differently during development in Phase 3?
During Phase 3, the group intends to improve communication and collaboration to ensure that all members understand their responsibilities, progress and deadlines. Regular progress updates and more frequent group discussions will help members identify problems earlier and reduce misunderstandings. The group will also aim to work together more consistently, provide assistance when members encounter difficulties and ensure that assigned tasks are completed on time. Responsibilities and deadlines will be communicated clearly, and the project schedule will be updated regularly to monitor progress. In addition, the group will seek consultations and feedback when necessary and use the Phase 2 design documents as a guide during implementation. The system architecture, UML diagrams, ERD and prototypes will help ensure that the web and mobile applications are developed according to the planned requirements. By improving communication, time management, teamwork and task coordination, the group aims to make the development process more organised and ensure that the web and mobile applications work together as one integrated system.